| # | Phase / Task Group | Detailed Tasks | Primary Role |
| --- | --- | --- | --- |
| 1 | Environment & Tool Installation | Install Power BI Report Builder Set up DevOps repo | Developer, DBA, Power BI Team 1 Day |
| 2 | Discovery & Analysis | Inventory 10 Crystal Reports; Extract SPs/views/functions; Document parameters, grouping, formulas; Identify shared headers/footers | Developer, DBA 3 days |
| 3 | Database Preparation | Refactor SPs/functions for RDL compatibility Create new views | DBA, Developer 1 days |
| 4 | RDL Development | Build RDL layout (tablix, headers, footers) Recreate Crystal formulas in CES web app Database integration | Developer, DBA (support) 12 days |
| 5 | ASP.NET Core Integration | Configure Power BI REST API Implement secure token generation (AAD) Implement PDF export endpoint (ExportToFile API) Bind parameters to UI | Developer 1 days |
| 6 | Deployment to Power BI Service | Configure data source credentials Bind datasets to gateway Assign workspace permissions | Developer Power BI Team 3 days |
| 7 | QA Testing | Side-by-side comparison (Crystal vs RDL PDFs); | QA, Developer 7 days |
| 8 | UAT Testing | Confirm PDF layout accuracy Validate data correctness | Business Users, BA, Developer 5 days |
| 9 | Production Deployment | Publish final RDLs Update ASP.NET Core configuration Migrate Views, Stored proc, functions | Developer, Power BI Team, DBA 2 days |

CES Power-BI migration high-level tasks and efforts estimates.

Assumptions :

- Reports will be like to like (minor changes are acceptable)

- Reports will be in PDF format, No dashboard changes anticipated.